- Amitabha Pure Land Empowerment

- 5/12/2001 – 5/13/2001    Chung-Yen Monastery

| # Time \ Date | # Sat 5/12/01 | Sun. 5/13/01 | Remarks |
| --- | --- | --- | --- |
| 08:15 | T: move lodging students and volunteers’ cars to designated parking area C: distribute walkietalkies, bottle water, battery |  |  |
| 08:30 | A: process walk-in registration reissue lost tickets accept prayer request T/ M:direct student cars to designated parking area |  |  |
| 08:45 | AV: turn on outdoor PA R: ready for HEKC's arrival T: radio back when motorcade arrives All: welcome HEKC at GBH stairs |  | . |
| 09:00 | P: H.E. Karma Chagme Rinpoche arrives |  |  |
| 09:30 | R: check ticket at doors hand out welcome kit and recitation booklet AV: turn on indoor PA, start mantra chanting CD |  |  |
| 09:55 | P: short announcement, welcome speech |  |  |
| 10:00 | R: close side doors, put on "do not disturb" sign P: initial prayer, teaching M: pull people from traffice control to Kitchen | P: teaching |  |
| 12:00 | P: lunch in Dining Hall |  |  |
| 12:30 | M: remove dining area trash |  |  |
| 12:45 | M: line up seats, clean restrooms |  |  |
| 01:30 | R: check ticket at doors AV: start mantra chanting CD | (To be arranged: HEKC greets all volunteers) |  |
| 02:00 | P: teaching R: close side doors, put on "do not disturb" sign | P: empowerment |  |
| 02:15 | A: stop accepting prayer request prepare name list calculate income and expenses | R: hand out sadhana?, photo |  |
| 04:00 | P: break | P: closing speech offering for Ripoches and CYM sangha |  |
| 04:30 | P: Amitabha Jangchog Puja | P: Consultation S/M: Clean up |  |
| 06:00 | P: HEKC leaves CYM T: direct student cars leaving M: line up seats, clean restrooms, remove trash |  |  |
| 06:30 | C: collect walkietalkies |  |  |
| 07:00 | K: dinner |  |  |

P: Program (Shou-Ling Peng) 	R: reception (Chu How) 		M: mobil (Tsu-Ku Lee)

AV: (Wei Lai / S-L Peng) 	K: kichen  (Chin-Feng Lai)	A: registration/accounting (Yoke Kwan / Hsiu-Hui Lin)

C: communication  (Wei Lai)	T: traffic control (Gary Li)		S: site arrangement (Mark Mei)